## Sheet1
SECP3133 HPDP Section 02
Group: 5
Project 2
Group Members |  | Matrics No
Camily Tang Jia Lei |  | A22EC0039
Muhammad Luqman Hakim |  | A22EC0086
Ng Shu Yu |  | A22EC0228
Wong Qiao Ying |  | A22EC0118
No. | Date | Activity / Task Description | PIC | Results
1 | 15/06/2025 | Initial meeting and discussion on project scope and roles | All members | Project objectives clarified; responsibilities assigned
2 | 16/06/2025 | Environment setup: Docker installation, VS Code config, project repo initialized | Wong Qiao Ying | Local development environment ready
3 | 17/06/2025 | Kafka, Zookeeper, Elasticsearch, Kibana containers setup | Wong Qiao Ying | Backend services launched via Docker Compose
4 | 18/06/2025 | Verified connectivity between services (Kafka, ES, Kibana) | Wong Qiao Ying | Services integrated and working properly
5 | 19/06/2025 | Web scraping prototype using Playwright for batch article retrieval | Camily Tang Jia Lei | Batch scraper script functional and retrieves articles successfully
6 | 20/06/2025 | NLTK-based preprocessing + VADER labeling implemented | Camily Tang Jia Lei | Articles labeled into sentiment classes (positive, neutral, negative)
7 | 21/06/2025 | Spark ML pipeline created for Logistic Regression sentiment model | Camily Tang Jia Lei | Spark model trained and saved to disk
8 | 22/06/2025 | Developed LSTM sentiment classification model using TensorFlow/Keras | Camily Tang Jia Lei | Keras model trained and evaluated
9 | 23/06/2025 | Real-time live scraper using Playwright + Kafka producer completed | Wong Qiao Ying | Live articles now being streamed into Kafka topic
10 | 24/06/2025 | Live predictor service using Spark + LSTM + Kafka consumer completed | Camily Tang Jia Lei | Real-time predictions pushed to Elasticsearch
11 | 25/06/2025 | Initial dashboard design using Kibana (index pattern setup, basic panels) | Ng Shu Yu | Dashboard connected to live_predictions index
12 | 26/06/2025 | Enhanced Kibana dashboard: added pie charts, sentiment distribution, time series | Ng Shu Yu | Dashboard provides interactive sentiment insights
13 | 27/06/2025 | Conducted model evaluation: f1-score, accuracy, confusion matrix analysis | Camily Tang Jia Lei | Metrics reported for Spark and LSTM models
14 | 28/06/2025 | Created visualizations of probability distributions using bar charts | Ng Shu Yu | Visual evidence of prediction confidence captured
15 | 29/06/2025 | Began writing report sections 2.0–3.3 (data collection, models, training) | Luqman & Ng Shu Yu | Draft report in progress
16 | 30/06/2025 | Wrote evaluation and performance section (section 4–5) | Luqman & Ng Shu Yu | Included classification tables, accuracy descriptions
17 | 2025-01-07 | Compared batch vs real-time results and model latency | Luqman | Concluded LSTM outperforms in real-time; Spark good in batch
18 | 2025-02-07 | Finalized discussion and optimization section (section 6) | Luqman & Ng Shu Yu | Added analysis of architecture and evaluation summary
19 | 2025-03-07 | Wrote conclusion and proposed future enhancements (section 7) | Luqman | Final section written with summary and suggested improvements
20 | 2025-09-07 | Final proofreading, formatting, and submission of report | Camily Tang Jia Lei | Report finalized and ready for submission